## About
ABOUT THIS GANTT CHART
Visualise and track your projects using this Gantt chart template. To start, enter the tasks you're working on in the Milestone Description section and then enter details for each task. The data will automatically update and it’s easy to insert new tasks or use the scrollbar to scroll through the timeline.
• Use Progress to add how much of the project you finished by adding a percentage number. • Add the day you started your project in the Start Date. • Finish your calculations by filling in the number of days you need to complete your project in the No. of Days field.

## Light
T470
| Aard |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Nathanial Norburrn
| Project Start Date: | 2022-02-05 |  |  |  |  | May | [20 empty] | June | [27 empty] | July
| Scrolling Increment: | 100 | time axis 2022-05-16 to 2022-07-10
| Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2022-05-16 to 2022-07-10
Pre Start Work
| Plan Project with Aard | Goal | NN / SN / DM/PG | 100% | 2022-02-05 | -20
| Review content on forums | On Track | NN | 100% | 2022-02-05 | 20 | bar: 2022-05-18
Start Formal Project
| Agree scope of work with Aard | Milestone | NN/SJN | 100`% | 2022-02-25 | 1
| Review original source code | On Track | NN/SJN | 100% | 2022-02-26 | 3
| Analyse Code to Identify Tasks | On Track | NN/SJN | 100% | 2022-03-01 | 4
| TMA 01 | On Track |  | 100% | 2022-03-05 | 10
| Section 3.1 | On Track | NN | 100% | 2022-03-07 | 4
| Section 3.2 | On Track | NN | 100% | 2022-03-12 | 4
| Section 3.3 | On Track | NN | 100% | 2022-03-14 | 2
| TMA 01 Complete | Milestone |  |  | 2022-03-15 | 0
Restart Project as Army Loader
| Create SQL insert Statements (6.6) [1/2 Aard] | On Track | NN/SJN | 100% | 2022-03-15 | 2
| Create CRUD statements on SQL Server | On Track | NN | 100% | 2022-03-17 | 2
| Create and populate remote database | On Track | NN | 100% | 2022-03-19 | 6
Build Original Version (6.7)
| Set up DOSBOX | On Track | NN |  | 2022-03-25 | 2
| Install and run Microsoft PDS | On Track | NN |  | 2022-03-27 | 1
| Modify original PDS files | On Track | NN |  | 2022-03-28 | 1
| Build Original Version | Milestone | NN | 0% | 2022-03-29 | 1
TMA 02 | TMA02 | Milestone | NN | 100% | 2022-05-02 | 15
Making the Website
| Add the 36 models (6.8) | On Track | NN | 100% | 2022-05-17 | 6 | bar: 2022-06-14 to 2022-06-20
Add the helpers (6.9)
| Add ChangeNodeHelper | On Track | NN | 100% | 2022-05-23 | 1 | bar: 2022-06-21
| Add ConnectionHelper | On Track | AARD | 100% | 2022-05-24 | 0
| Add Enums | On Track | NN | 100% | 2022-05-24 | 2 | bar: 2022-06-22 to 2022-06-23
| Add EnumExtensions | On Track | NN | 100% | 2022-05-26 | 1 | bar: 2022-06-24
| Add FindNodeHelper | On Track | NN | 100% | 2022-05-27 | 1 | bar: 2022-06-25
| Add IDisposableHelper | On Track | AARD | 100% | 2022-05-28 | 0 | bar: 2022-06-26
| Add RNG | On Track | NN | 100% | 2022-05-28 | 0 | bar: 2022-06-26
| Add UndoHelper | High Risk | NN | 50% | 2022-05-28 | 4 | bar: 2022-06-27 to 2022-06-30
Add the makers (6.10)
| Add ArmyOfficerMaker | On Track | NN | 100% | 2022-06-01 | 8 | bar: 2022-07-01 to 2022-07-08
| Add CommonValuesExtractor | On Track | NN | 100% | 2022-06-09 | 2 | bar: 2022-07-09 to 2022-07-10
| Add DisplayMaker (Debug Code) | On Track | NN | 100% | 2022-06-11 | 1
| Add NameMaker | On Track | NN | 100% | 2022-06-12 | 12
| Add UnitNameMaker | On Track | NN | 100% | 2022-06-24 | 2
| Add UnitOfficerMaker | On Track | NN | 100% | 2022-06-26 | 3
Create Basic Website (6.11)
| Make Hamburger menu (6.11) | On Track | NN | 100% | 2022-06-29 | 5
Add Create Functionality (6.12)
| Add Select an area | On Track | NN | 100% | 2022-07-04 | 2
| Add Select an army | On Track | NN | 100% | 2022-07-06 | 3
| Add Officer | On Track | NN | 100% | 2022-07-09 | 2
| Add Troops | On Track | NN | 100% | 2022-07-11 | 4
| Add Load and Save (6.12.13) | On Track | AARD | 100% | 2022-07-15 | 3
tma03 | TMA03 | Milestone | NN | 100% | 2022-07-18 | 12
The project stopped here and restarted in March 2023
| The Treeview (6.14) | On Track | NN | 100% | 2023-03-03 | 4
| Drag and Drop (6.15) | On Track | NN | 100% | 2023-03-07 | 2
| Editing Units (6.16) | On Track | NN | 100% | 2023-03-09 | 3
| Adding Units 6.17) | On Track | NN | 100% | 2023-03-12 | 2
| Removing Units (6.18) | High Risk | NN | 50% | 2023-03-14 | 3
| Write up and submission | Goal | NN | 100% | 2023-03-17 | 15
To add more data, Insert new rows ABOVE this one

## Dark
PROJECT TITLE
Company name |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project lead
Project Start Date: | 2023-04-17 |  |  |  |  | April | [13 empty] | May | [34 empty] | June
Scrolling Increment: | 1 | time axis 2023-04-18 to 2023-06-12
Milestone description | Category | Assigned to | Progress | Start | Days | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M
TITLE 1
Task 1 | Goal | Name | 25% | 2023-04-17 | 3 | T: 2; W: 2
Task 2 | Milestone |  |  | 2023-04-22 | 1 | bar: S
Task 3 | Low Risk |  | 50% | 2023-04-14 | 10
Task 4 | Milestone |  |  | 2023-05-07 | 1 | bar: S
Task 5 | Med Risk |  | 10% | 2023-04-23 | 6
TITLE 2
Task 1 | High Risk |  | 60% | 2023-04-23 | 13
Task 2 | On Track |  | 50% | 2023-04-25 | 9
Task 3 | Low Risk |  | 33% | 2023-04-30 | 11
Task 4 | Milestone |  |  | 2023-05-02 | 1 | bar: T
Task 5 |  |  |  | 2023-05-03 | 24
TITLE 3
Task 1 | On Track |  |  | 2023-05-02 | 4
Task 2 | Med Risk |  |  | 2023-05-05 | 14
Task 3 | On Track |  |  | 2023-05-20 | 6
Task 4 | Goal |  |  | 2023-05-24 | 3 | W: 2; T: 2; F: 2
Task 5 | Low Risk |  |  | 2023-04-23 | 19
TITLE 4
Task 1 |  |  |  | 2023-05-27 | 15
Task 2 |  |  |  | 2023-06-10 | 5
Task 3 | Milestone |  |  | 2023-07-22 | 1
Task 4
Task 5
To add more data, Insert new rows ABOVE this one

## Colour
PROJECT TITLE
Company name |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project lead
Project Start Date: | 2023-04-17 |  |  |  |  | April | [13 empty] | May | [27 empty] | June
Scrolling Increment: | 5 | time axis 2023-04-22 to 2023-06-16
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2023-04-22 to 2023-06-16
TITLE 1
Task 1 | Goal | Name | 25% | 2023-04-17 | 3
Task 2 | Milestone |  |  | 2023-04-22 | 1 | bar: 2023-04-22
Task 3 | Low Risk |  | 50% | 2023-04-14 | 10
Task 4 | Milestone |  |  | 2023-05-07 | 1 | bar: 2023-05-07
Task 5 | Med Risk |  | 10% | 2023-04-23 | 6
TITLE 2
Task 1 | High Risk |  | 60% | 2023-04-23 | 13
Task 2 | On Track |  | 50% | 2023-04-25 | 9
Task 3 | Low Risk |  | 33% | 2023-04-30 | 11
Task 4 | Milestone |  |  | 2023-05-02 | 1 | bar: 2023-05-02
Task 5 |  |  |  | 2023-05-03 | 24
TITLE 3
Task 1 | On Track |  |  | 2023-05-02 | 4
Task 2 | Med Risk |  |  | 2023-05-05 | 14
Task 3 | On Track |  |  | 2023-05-20 | 6
Task 4 | Goal |  |  | 2023-05-24 | 3 | 2023-05-24: 2; 2023-05-25: 2; 2023-05-26: 2
Task 5 | Low Risk |  |  | 2023-04-23 | 19
TITLE 4
Task 1 |  |  |  | 2023-05-27 | 15
Task 2 |  |  |  | 2023-06-10 | 5
Task 3 | Milestone |  |  | 2023-07-22 | 1
Task 4
Task 5
To add more data, Insert new rows ABOVE this one